## Project Planner
Airbnb Data Analysis Software
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 25 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Initiating | bar: PERIODS 1
1.1. Assign Project Manager | 1 | 1 | 1 | 1 | 100% | bar: PERIODS 1 to PERIODS 2; PERIODS 8
2. Planning
2.1. Create Scope Plan | 1 | 7 | 1 | 7 | 100%
2.2. Create WBS and Schedule | 1 | 7 | 1 | 7 | 100%
2.3 Software Requirements | 7 | 8 | 7 | 8 | 100%
2.4 User Requirements | 7 | 8 | 7 | 8 | 100%
2.5 Use cases& diagrams | 7 | 8 | 7 | 5 | 100%
3.Designing
3.1. UI design | 14 | 2 | 10 | 2 | 100% | bar: PERIODS 9 to PERIODS 13
3.2. Wireframes | 16 | 3 | 16 | 3 | 100% | bar: PERIODS 15 to PERIODS 16
3.3. Problem Background | 16 | 3 | 16 | 3 | 100% | bar: PERIODS 12 to PERIODS 16
3.4. Software Design | 16 | 3 | 16 | 3 | 100% | bar: PERIODS 13 to PERIODS 15
3.5 System Overview | 19 | 5 | 19 | 4 | 100%
3.6 Potential Benefits | 19 | 5 | 19 | 4 | 100%
3.7 System Components | 19 | 5 | 19 | 5 | 100% | bar: PERIODS 7 to PERIODS 8; PERIODS 12 to PERIODS 13
4. Executing
4.1. Collect the raw data | 24 | 1 | 24 | 1 | 100%
4.2. Retrieve the data | 24 | 7 | 24 | 7 | 100%
4.3. Front-end Implementation | 24 | 10 | 24 | 10 | 100%
4.4. Back-end Implementation | 34 | 10 | 34 | 10 | 100%
4.5. Database schema creation | 38 | 6 | 38 | 6 | 100%
4.6. Business logic implementation | 44 | 3 | 44 | 3 | 100%
5. Controlling
5.1. Testing the software | 24 | 23 | 24 | 23 | 100%
5.2. Software testing reports | 47 | 3 | 47 | 3 | 100%
6. Finalising
6.1. Final Report | 50 | 10 | 50 | 10 | 100%